## Sheet1
| N20 | N21 | N22 | N23 | N26 | N27 | N28 | N29 | N30 | D03 | D04
Preparation and Planning
Develop Game Plan | bar: N20 to N21
Finish UML Chart | bar: N21
Approved and ready for coding | bar: N22
Coding
Make Character/Boss Creation Class | bar: N22 to N26
Make Inventory Class | bar: N22 to N26
Attack Method | bar: N27 to N29
Boss Method | bar: N27 to N29
Shop Method | bar: N27 to N29
Game is playable | bar: N29
Commenting
Comment code | bar: N30
Revision
Test the game | bar: D03
Make necessary changes | bar: D04
Have game finished and presentable | bar: D04